## Лист1
TASK | START DATE | END DATE | DURATION | STEP
Research & understand datavisApp under the hood | 2024-06-01 | 2024-06-02 | 1 | 1. Preparation & research
Finish case study | 2024-06-02 | 2024-06-03 | 1
Create Gantt chart | 2024-06-03 | 2024-06-06 | 3
Brainstorm ideas and note the best ones | 2024-06-04 | 2024-06-10 | 6
Сonsider interface design changes | 2024-06-04 | 2024-06-10 | 6
Find & modify data (~2) | 2024-06-15 | 2024-06-16 | 1 | 2. Development Phase
Finish the first vis | 2024-06-16 | 2024-06-19 | 3
Finish the second vis | 2024-06-20 | 2024-06-25 | 5
Upgrade "tech-diversity-race" | 2024-06-27 | 2024-06-29 | 2 | 3. Upgrade
Upgrade "pay-gap-by-job-2017" | 2024-06-29 | 2024-07-01 | 2
Upgrade main design of app | 2024-07-01 | 2024-07-03 | 2
Clear & fix code | 2024-07-03 | 2024-07-06 | 3
Testing | 2024-07-03 | 2024-07-06 | 3
Planning Gantt chart after midterm | 2024-07-06 | 2024-07-07 | 1
Submit final project | 2024-07-06 | 2024-07-07 | 1 | 4. Midterm